## Product & Sprint Backlog
ID | Summary | Estimate | Sprint1 | Sprint2 | Sprint3 | Sprint4
gc-1 | Display main window | 3 | Done
gc-2 | Display table with static fields and default values | 5 | In progress | Done
gc-3 | Display and Total Grade with default value | 2 | Done
gc-4 | Display buttons without associated actions | 2 | Done
gc-5 | Enter attendence grade | 3 |  | Done
gc-6 | Enter assignment grades | 8 |  | In Progress | Done
gc-7 | Enter project grades | 8 |  | In Progress | Done
gc-8 | Enter mid-term exam grade | 3 |  | Done
gc-9 | Enter final exame grade | 3 |  |  | Done
gc-10 | Display calcualted Total Grade | 5 |  |  | Done
gc-11 | Change group weight | 5
gc-12 | Import grades for a student | Medium
gc-13 | Export grades for a student | Medium
gc-14 | Import grades for multiple students
gc-15 | Export grades for multiple students